## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | overall tablet experience good/great | 72% customers rated good/great
Customers | Went well | customers wanted the traditional waitering system back | 10% opted for this | leave room for adaptation to change, offer an option on tablet to select a waiter
Customers | Went well | checkout process quick, easy and secure | 82% customers selected yes for the same statement
Customers | Went well | Waitstaff educating customers on tablet use | 76% opted very well, 14% opted ok
Customers | Went well | The tablet navigation experience | 48%(very easy/fairly easy), 30 neutral | Work with designer to enhance the user ease of use
Customers | Went well | Good tablet implememtation feedback | - The tablets were fun!- I liked the tablets- it felt like we got through our dinner faster
Customers | Went well | Newletter sign up
Customers | Needs improvement | The time it takes to serve an order | 44% received food after 20+ minutes | Work with GMs to speed up the order ready process
Customers | Needs improvement | The order not meeting the customers demands | 28% customers had issues with this | Work to improve the custimization feature and making it pripority for kitchen staff to view.
Customers | Needs improvement | Tablet malfunction | 12% faced technical issues | Work on checking the tablets are working properly once before the start of the day, provide replacement tablets for the one's facing continous errors
Customers | Needs improvement | The wait time before getting a table | 54% had to wait for 15+ minutes | Work on inefficiencies in order served time, the collaboration between Boh, Foh staff
Project team | Went well | Tablet installations at differnet locations | Both GMs observations(retrospective meeting)
Project team | Went well | Meet most of our customer satisfaction standards | Peta: data shows we listen to our customers(Retrospective meeting)
Project team | Went well | Guests got hang of the tablets | as stated by Gilly in meeting
Project team | Went well | Payments through tablets | Gilly: payments worked for the most part(retrospective meeting)
Project team | Went well | Vendor cadence was benefical | Peta:weekly calls with vendors helped us stay on track and clarify task dependencies.(Retrospective meeting) | Asking vendors to maintain the same cadence
Project team | Went well | Tickets came in smoothly | Zane:Tickets came through at a good pace and were easy to keep track of(retrospective meeting)
Project team | Went well | Collecting survey data | Peta:the survey was able to capture meaningful data(retrospective meeting)
Project team | Needs improvement | Few internal operational issues, hindered teams ability to carry out tasks smoothely | Peta:we started implementing the tablets and training, we discovered a few internal operational issues that we hadn’t planned for.(Retrospective meeting) | next rollout, we want to do a better job of understanding each location’s history before planning gets underway.
Project team | Needs improvement | Food orders getting sent back | Both Zanes and Larrisa's observation(retrospective meeting) | Prioritizing this issue for further analysis
Project team | Needs improvement | Not much decrease inTable turn time | Gilly:One area we could still improve is table turn time(retrospective meeting)
Project team | Needs improvement | confusions between boh and foh | larrisa:lack of understanding between what the front of house staff does and the back of house staff does.(Retrospective meeting) | take time to share those experiences it will help everyone work together more effectively, reducing the tendency to blame each other
Project team | Needs improvement | routine maintenance issues | Seydou:There will always be routine maintenance issues that pop up—it just comes with the territory(Retrospective meeting) | usually easy to manage once you identify what type of issue you’re dealing with, also update the process manual for soultions to these issues
Project team | Needs improvement | Less sign up for birthday club | Only 16% signed up, data shows | grow the participant list. work with the designer to update the content on the website and the tablets so it’s clearer what the program is, what we’re asking, and how people can participate.
Project team | Needs improvement | Some vacation time not considered in planning took more time to install tablets | Seydou:add that tablet implementation took just a little bit longer than we hoped.(retrospective meeting) | Plan things properly next time, keeping in mind everyone's availablity
Project team | Needs improvement | not prepared for large volume of orders | we’d like to do a bit more to help the back of house staff scale up their operations before the main launch | Include in the next planning to emphasize on Boh order load capacity
Project team | Needs improvement | need to enhance the waitstaff training process | Waitstaff training process(retrospective meeting) | develop a more comprehensive training session, or even break the training up into two parts