## Slide 1: Tablet Rollout Test Run Milestone: Restaurant pilot launched

## Slide 2
Summary
The test launch of the tablet rollout surveyed 50 customers. 72 percent of the customers had possitive experience with the tablet ordering system, signifying that we are moving in the positive direction with our project. 88 percent of the customers faced no technical issues which is close to our quality goal but still some refinements are required. Overall the staff was able to help the customers understand the ordering process, but still customer adaptation is ongoing. Only 10 percent of the customers wanted to go back to the traditional way of ordering through waiters which indicates the overall success of our tablet initiative as to increase the customers experience.

## Slide 3
Overview
Did we achieve our goals?
Were customers satisfied?
In order to evaluate the tablet launch, we asked guests to complete a survey on the tablet at the end of their visit.

## Slide 4
Findings
Chart: Order Served Time
| 0-20min. | 21-30min. | 31-40min | 41-50min. | 50+min
Average Ticket Time | 28 | 15 | 6 | 1 | 0
One of the major things we have address is the time it takes to serve an order. As per the findings
only 56% of orders are served in 0-20 minutes, far away from our quality standard of having
8 minutes for appetizers and 10-15 minutes for entrees. Would also like to stay that due to this our
Customer wait time in the lobby is also being negatively effected. We need to speed up our order preparation process, and decrease the percentage of any order taking more than 20 minutes.

## Slide 5
Next Steps
Survey Finding: Table turn time didn’t decrease
Recommendation: Work with GMs on speeding up guest visits, and also address the time it takes to serve an order.

## Slide 6
Next Steps
Survey Finding: Order accuracy issues
Recommendation: Check with the Foh and Boh staff to see where the issues are. Also make sure the customization feature in the tablets are working fine and reduce any table malfunctions.