## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status
Milestone 1: Tablets received
research tablet rollout options | Take help of seydou |  |  | 1
Generate quotes and review costs |  |  |  | 3
Create contract and SoW for vendors |  |  |  | 7
Order Tablets | 7 days shipment, 2-3 days buffer, 1 day broken pieces replacement |  |  | 10
Milestone 2:Tablet Installation
Schedule an electrician for wiring | Consult Deanna, will take 16hrs for both location, but the restaurant can't be closed for whole day, so two half days are planned |  |  | 2
Install tablets in bar area at North location |  |  |  | 1
Install tablets in bar area at Downtown location |  |  |  | 1
Sync tablet software with POS | If POS is up to date for integration will take few hours, Gilly is called to check on the current version |  |  | 1
Milestone 3: Menu Simplification
upload menu branding on tablets | Connect Sauce & Spoon marketing team with Terrific tablets |  |  | 14
Load menus in tablet | Waiting on Carter |  |  | 7
Mockups of items with coupons and coupon values | Few hours when the coupun and value is known |  |  | 1
Make menu accessible to the visually impaired |  |  |  | 7
Milestone 4: Training
Devicing training plan for GM | seydeo trains, 2 hr, one hour before and after each training for facilitator prep/debrief |  |  | 5
Training for group of managers | One day event |  |  | 1
Gm meeting for waitstaff buy in | Let Gilly plan this, one hr at each location |  |  | 1
Devicing training plan for waitstaff | One day event |  |  | 5
Training for waitstaff | 2hr each by GM at each location, one hour before and after each training for facilitator prep/debrief |  |  | 1
Create post dinning survey |  |  |  | 3
Invite friends and family to do a test run of the tablets | One day event |  |  | 1
Implement post dinning survey |  |  |  | 0
Milestone 5: Securing tablet system
Enable GPS location services on each tablet |  |  |  | 1
Create a procedure for securing tablets at the end of the night | One day event |  |  | 1
Create messaging about payment portal security to display on tablets | Uploading text |  |  | 1
Milestone 6:Launch
Create a launch day plan: staffing, troubleshooting etc |  |  |  | 20
Educate customers to the new tablet system through emails | send to the email list of existing customers |  |  | 1
Launch day | One day event |  |  | 1

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone 1: Tablets received
research tablet rollout options | Take help of seydou | 1 | 1 | 1 | 1 | H
Generate quotes and review costs |  | 3 | 1 | 3 | 7 | H
Create contract and SoW for vendors |  | 7
Order Tablets | 7 days shipment, 2-3 days buffer, 1 day broken pieces replacement | 10 | 7 | 8 | 10 | H
Milestone 2:Tablet Installation
Schedule an electrician for wiring | Consult Deanna, will take 16hrs for both location, but the restaurant can't be closed for whole day, so two half days are planned | 2 | 1 | 2 | 4 | M
Install tablets in bar area at North location |  | 1
Install tablets in bar area at Downtown location |  | 1
Sync tablet software with POS | If POS is up to date for integration will take few hours, Gilly is called to check on the current version | 1 | 1 | 3 | 4 | L
Milestone 3: Menu Simplification
upload menu branding on tablets | Connect Sauce & Spoon marketing team with Terrific tablets | 14
Load menus in tablet | Waiting on Carter | 7 | 3 | 7 | 14
Mockups of items with coupons and coupon values | Few hours when the coupun and value is known | 1
Make menu accessible to the visually impaired |  | 7
Milestone 4: Training |  |  | 10 | 14 | 21 | H
Devicing training plan for GM | seydeo trains, 2 hr, one hour before and after each training for facilitator prep/debrief | 5
Training for group of managers | One day event | 1
Gm meeting for waitstaff buy in | Let Gilly plan this, one hr at each location | 1
Devicing training plan for waitstaff | One day event | 5
Training for waitstaff | 2hr each by GM at each location, one hour before and after each training for facilitator prep/debrief | 1
Invite friends and family to do a test run of the tablets | One day event | 1
Milestone 5: Securing tablet system
Enable GPS location services on each tablet |  | 1
Create a procedure for securing tablets at the end of the night | One day event | 1
Create messaging about payment portal security to display on tablets | Uploading text | 1
Milestone 6:Launch
Create a launch day plan: staffing, troubleshooting etc |  | 20 | 14 | 20 | 23 | L
Educate customers to the new tablet system through emails | send to the email list of existing customers | 1 | 1 | 1 | 2 | H
Launch day | One day event | 1 | 1 | 1 | 1 | H
Create and implement post dining survey

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
your-restaurants-order-taking-process
Whole capstone solution

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | average ticket time 8 minutes for appetizers, 12-15 minutes for entrees | Was the ticket time for the locations decreased? | Ticket times | FALSE
Customer Satisfaction | Have one minute checkout time | Did we learn any new pattern in the customer satisfaction? | Customer satisfaction | FALSE
Customer Satisfaction | < 5% customer complaints about technical issues due to tablets | How can we increase the ease of use of the tablets? | Technical compliants registered | FALSE
Customer Satisfaction | 98% order accuracy | Were the customers able to benefit from the ordering process? | decrease in average comping percent | FALSE
Customer Satisfaction | Lobby wait time of 10 minutes or less | How can we improve the customer waiting time? | increase in average order accuracy | FALSE
Customer Satisfaction | Increase customer retention in tablet areas by 5% | Should we continue using tablets? | Guests who used tablets are 50% more likely to recommend the restaurant to a friend | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
average ticket time 8 minutes for appetizers, 12-15 minutes for entrees | Was the ticket time for the locations decreased? | Ticket times | What was the main categories you ordered | Multiple choice | appetizers | main entrees | both
|  |  | While your were ordering, Did you use tablet for your order | True/False | TRUE | FALSE
|  |  | How much time it took to receive your order | Multiple choice | <= 8 minutes | <=12/15 minutes | > 15 minutes
|  |  | On a scale of one to five, how satisfied were you with your order | Scaled | 1:Very Satisfied | 2:Somewhat satisfied | 3:Neither satisfied nor dissatisfied | 4:Somewhat satissfied | 5:Very dissatisfied
Have one minute checkout time | Did we learn any new pattern in the customer satisfaction? | Customer satisfaction | Were you satisfied with the ease of use of the checkout process | Yes/No | Yes | No
|  |  | What can added to the existing checkout system to increase user experience | Open-ended | Open-ended
|  |  | Were there times you felt lost in the process? | Yes/No | Yes | No
< 5% customer complaints about technical issues due to tablets | How can we increase the ease of use of the tablets? | Technical compliants registered | Did you face any technical issues while using tablets | True/False | TRUE | FALSE
|  |  | Was the staff present able to help you resolve the issue | Yes/No | Yes | No
|  |  | On a scale of one to five, how satisfied were you with the table system | Scaled | 1:Very Satisfied | 2:Somewhat satisfied | 3:Neither satisfied nor dissatisfied | 4:Somewhat satissfied | 5:Very dissatisfied
98% order accuracy | Were the customers able to benefit from the ordering process? | decrease in average comping percent | Was the order received the way you wanted it to be | True/False | TRUE | FALSE
Lobby wait time of 10 minutes or less | How can we improve the customer waiting time? | increase in average order accuracy | How long it took for you to get a table | Scaled | 0-5 min. | 6-10 min. | 11-15 min. | 15+ min.
Increase customer retention in tablet areas by 5% | Should we continue using tablets? | Guests who used tablets are 50% more likely to recommend the restaurant to a friend | Would you recommend our restaurant to friends and family after your experience | Yes/No | Yes | No